## Risks
Risk Management Matrix (Risk Register)
Project |  |  | Barbershop Management System | [5 empty] | Project # | 1001
Project manager |  |  | Emad Muhammad Abbasi | [5 empty] | Sponsor | Carlos Zuniga
Project artifacts | [8 empty] | Updated | 2025-02-21
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | Team is unfamiliarity with scheduling algorithms may cause development delays. | 3 | 4 | 3 | 72 | Technical | Slow development progress, repeated errors in scheduling logic | Research existing libraries, consult experts, conduct prototype testing | Adjust project timeline to allow for testing | Dev Team | Monitoring | 2025-02-21 | 2025-04-12
2 | There is a limited availability of test users from barber shop clientele | 3 | 3 | 4 | 72 | Resource | No feedback from users, testing phase delayed | Engage early testers, offer incentives | Use simulated test data if needed | Project Manager | Mitigation in progress | 2025-02-21 | 2025-04-12
3 | There is potential integration challenges between backend and frontend | 3 | 4 | 3 | 72 | Technical | API failures, front-end errors during integration | Establish clear API documentation, conduct early integration testing | Assign a dedicated developer for API troubleshooting | Lead Developer | Monitoring | 2025-02-21 | 2025-04-12
4 | There may be project schedule delays due to lack of defined timelines | 4 | 4 | 2 | 64 | Schedule | Missed internal deadlines, undefined milestones | Finalize and document project schedule | Adjust development phases if necessary | Project Manager | Open | 2025-02-21 | 2025-04-12
5 | There may be user authentication vulnerabilities could lead to data breaches | 3 | 5 | 3 | 90 | Security | Failed security tests, unauthorized access attempts | Implement strong authentication (JWT, 2FA), conduct security testing | Roll back updates in case of security issues | Dev Team | Mitigation in progress | 2025-02-21 | 2025-04-12
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
Note on C6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on L6: Options are: Open Closed

## Issues
Issues Log
Project |  | Barbershop Management System |  | Project # | 1002
Project manager |  | Emad Muhammad Abbasi |  | Sponsor | Carlos Zuniga
Project artifacts |  |  |  | Updated | 2025-02-21
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | AWS admin login issue: Members is experiencing difficulties logging into the AWS academy. | Potential delays in the backend and project task that require AWS access | Investigate login credentials and ensure members have account permissions | Isaiah | 2 | 2025-02-19 | 2025-02-23 | 2025-02-03
2 | Commit Front-End Issue: Front End Developer, Jeremiah was unable to commit front-end code to Github | Delaying front-end progress | Resolve repository permissions or local git configuration issues | Moshood | 2 | 2025-02-19 | 2025-02-23 | 2025-02-24
3 | Azure Kanban Usage Confusion: Project Manager unsure how to properly add tasks and manage workflow in Azure DevOps/Kanban board. | Delaying Sprint Creation | 1. Research Azure DevOps/Kanban board features (tutorials, docs). | Emad | 1 | 2025-02-03 | 2025-02-09 | 2025-02-10
4 | Azure Kanban Usage Confusion: Project Manager unsure how to properly add tasks and manage workflow in Azure DevOps/Kanban board. | Delaying Sprint Creation | 2. Schedule a quick team training/demo session. | Emad | 1 | 2025-02-03 | 2025-02-09 | 2025-02-10
5 | Azure Kanban Usage Confusion: Project Manager unsure how to properly add tasks and manage workflow in Azure DevOps/Kanban board. | Delaying Sprint Creation | 3. Standardize board columns and usage conventions. | Emad | 1 | 2025-02-03 | 2025-02-09 | 2025-02-10
6 | Front-End Issue: When changing the status of a appointment the start and end times are not converting from the 24 hour on the backend to 12 hour format made for front end. | Delaying front-end progress | Investigate front-end code relating to how date and time works. | Moshood | 3 | 2025-04-02 | 2025-04-03 | 2025-04-09
7 | Appointment Canellation/Resceduling Logic: Based on the current timeline, the project Manager is raising concern on the logic behind the feature mentioned above. Whether to add onto scope to incur complexity or go with a straightfoward first come first serve approach. | May or May not increase Load on developers, which leads to further complexity that may need to be addressed | 4. Project Manager will present solutions at this week's cadence and team will vote on approach | Emad | 1 | 2025-03-31 | 2025-04-06 | 2025-04-06
9
10
11
12
13
14
15
Note on F6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Decision
Decision Log
Project |  | Barbershop Management System | Project # | 1003
Project manager |  | Emad Muhammad Abbasi | Sponsor | Carlos Zuniga
Project artifacts |  |  | Updated | 2025-02-21
ID | Decision Description | Comments | Owner | Status | Date Entered
1 | Team decided to use a bootstrap theme for the front-end wireframes. | N/A | Isaiah | Completed | 2025-02-21
2 | Team decided to use AWS and MySQL for the technical infrastructure | N/A | Moshood | Completed | 2025-02-21
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on D6: Who made the decision?
Note on E6: Options are: Open Closed

## Change Control
Change Control Log
Project |  | Barbershop Management System |  |  |  | Project # | 1004
Project Manager |  | Emad Muhammad Abbasi |  |  |  | Sponsor | Carlos Zuniga (Barber)
Project Artifacts | [5 empty] | Updated
ID | Change Description | Priority | Originator | Date Entered | Date Assigned | Evaluator | Status | Date of Decision | Included in Rev. #
1 | A change control was submitted and approved to exclude the implementation of an integrated payment system (e.g., Stripe or custom API). After discussions with the team and sponsor, the decision was made to retain the barber's current offline payment method due to privacy concerns and the application not being hosted publicly. This change ensures client operations remain uninterrupted and keeps the project within scope and timeline constraints. | High | Development Team | 2025-04-07 | 2025-04-07 | Jose Martinez | Complete | 2025-04-09 | N/A
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on C6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on D6: Who identified the change needed?
Note on G6: Who will decide what action is taken on the change?
Note on H6: Options are: In review Rejected Deferred Approved
Note on J6: Options are: No Rev. #

## Assumptions and Constraint
Assumptions and Constraints
Project |  | Barbershop Management System | Project # | 1005
Project manager |  | Emad Muhammad Abbasi | Sponsor | Carlos Zuniga
Project artifacts |  |  | Updated | 2025-02-21
ID | Description | Comments | Type | Status | Date Entered
1 | There is only one barber. | N/A | Assumption | Monitoring | 2025-02-21
2 | There will no other barbers in the future. | N/A | Assumption | Monitoring | 2025-02-21
3 | There will be no need for client notifications. | N/A | Assumption | Monitoring | 2025-02-21
4 | There will be no need for internal payment processing. | N/A | Assumption | Monitoring | 2025-02-21
5 | There will be no need for reporting or analytics. | N/A | Assumption | Monitoring | 2025-02-21
6 | There will be no need for client to have personal accounts. | N/A | Assumption | Monitoring | 2025-02-21
7 | There will be a limited amount of client data. | N/A | Constraint | Monitoring | 2025-02-21
8 | The sponsor only is fluent in spanish. | N/A | Constraint | Monitoring | 2025-02-21
9
10
11
12
13
14
15
Note on D6: Options are: A: assumption C: constraint
Note on E6: Options are: Open Closed

## Parking Lot
Parking Lot
Project |  |  | Project # | 1006
Project manager |  | Emad Muhammad Abbasi | Sponsor | Carlos Zuniga (Barber)
Project artifacts |  |  | Updated
Date | Person Idenfying Issue | Issue | Responsible | Date to be resolved | Date to be resolved
Note on D6: Options are: A: assumption C: constraint
Note on E6: Options are: Open Closed
Note on F6: Options are: Open Closed