| Project |  |  |  |
| --- | --- | --- | --- |
| Project Name: | Barber Shop Management System | Baseline Deploy Date | March 3, 2025 |
| Executive Overview: | The Barber Shop Management System will be a web-based solution enabling Carlos Zuniga, a local barber, to manage appointments, customer information, and basic business data. The goal is to streamline daily operations, reduce scheduling conflicts, and enhance customer service. | Planned Deploy Date | April 14, 2025 |

| Key Stakeholders |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sponsor(s) | Program Manager |  |  |  |  |  |  |
|  | Jose Martinez |  |  |  |  |  |  |
| Project Team Members |  |  |  |  |  |  |  |
| Project Manager | APM | Solution Architect | Lead Developer | Product Owner | Developer | Developer |  |
| Emad Abbasi | Trinity Klein | Moshood Elias | Isaiah Morales | Anthony Perla | Jeremiah Jarina | Sarah Yao |  |

| Reporting Period: | <Week of reporting: April 7th – April 11th > |
| --- | --- |

| Project Status Overview |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Prior Period | Current Period | General Changes Since Last Reporting Period: |
| Overall |  |  | The project is on track and aligns with the defined scope and deliverables. The application is now fully functional across both frontend and backend components. This week, the team is conducting user testing to identify and resolve any final issues before submission. Final presentation preparation is well underway, with the business section nearly complete and the technical portion to follow post-testing. A change control order has been submitted and approved for updates to the payment logic. The team remains on schedule, with all major milestones either completed or in final execution. |

| Project Status Dashboard |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No major issues or risks identified. Critical path and cost on-schedule. |  |  |  | Issues or risks have been identified with potential impact to critical path and costs. |  | Issues or risks have been identified with clear impacts to the critical path and costs; lack of a plan that identifies critical path. |
|  |  | Prior Period |  | Current Period |  |  |  |  |  |
| Overall |  |  |  |  | The project is on track and aligns with the defined scope and deliverables. The application is now fully functional across both frontend and backend components. This week, the team is conducting user testing to identify and resolve any final issues before submission. Final presentation preparation is well underway, with the business section nearly complete and the technical portion to follow post-testing. |  |  |  |  |
| Schedule: |  |  |  |  | The project remains on schedule, with all planned sprints and deliverables progressing as outlined in the charter. To support final integration, testing, and presentation prep, the team has increased its cadence from bi-weekly meetings to flexible, on-demand collaboration sessions to ensure timely completion and quality assurance. |  |  |  |  |
| Budget: |  |  |  |  | Budget is allocated well. There is no risk in the budget of the project. No monthly costs or added costs. |  |  |  |  |
| Scope: |  |  |  |  | The project remains within the approved scope following a submitted and accepted change control order regarding the payment logic. Due to privacy and security concerns, the team and sponsor agreed to continue using the barber’s current offline payment method, ruling out Stripe and custom API solutions. Additionally, while there were initial concerns about delivering a full analytics dashboard, scope alignment was restored through scope reprioritization and focused development. All core features—appointment scheduling, customer management, authentication, and basic reporting—are completed and meet the defined project objectives. |  |  |  |  |
| Resources: |  |  |  |  | Resources are allocated well. We have the time, skills, and knowledge to complete this project to deploy. There is no conflict. Everyone communicates professionally together. |  |  |  |  |

| Project (Short-term) Activities |  |  |
| --- | --- | --- |
| Key Activities Prior Period | Key Activities this Reporting Period | Planned Activities for Next Reporting Period |
| Complete full integration of appointment scheduling UI with backend logic. Conduct internal team testing of authentication and scheduling functions. Enhance customer profile management features. Conduct mid-sprint testing and gather feedback for adjustments. | Conduct final sprint testing. Complete any final items in the backlog (integration with frontend and backend). Gather feedback for adjustments. Finalize project documentation and deliverables. Complete project presentation. Complete technical documentation. | The team will conduct final user testing to validate functionality and address any remaining issues. Concurrently, we will finalize both the business and technical sections of the capstone presentation. All source code, documentation, and deliverables will be compiled and organized in preparation for final project submission and the end-of-semester presentation. |

| Current Project Risk |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Category | Risks | Impact 1-5 | Likelihood 1-5 | Total Risk Score | Mitigation | Risk Trigger | Risk Trigger Date | Risk Mitigation Owner | Risk Status | Comments / Action Status |
| 1 | Resource | Limited availability of test user and dummy data | 3 | 3 | Medium | Engage early test users from various sources. | Testing phase | TBD | Project Manager | Mitigation | Use free resources and AWS Learner Labs to our advantage. |
| 2 | Technical | Unfamiliarity with scheduling algorithms | 4 | 3 | High | Research and test available libraries | Backend development phase | TBD | Developers | Mitigation | Keep it simple, but effective. |
| 3 | Technical | Potential integration challenges between backend and frontend | 4 | 3 | High | Establish clear API documentation and conduct early testing | Development phase | TBD | Developers | Monitoring | Early integration tests have been planned. |
| 4 | Schedule | Project schedule delays possible due to lack of defined timelines | 4 | 4 | High | Finalize and document project schedule | Missed internal deadlines, undefined milestones | TBD | Project Manager | Open | Adjust development phases as needed. |
| 5 | Security | Potential possibility with a data breach of client information | 3 | 5 | Medium | Implement strong authentication, and conduct security testing | Failed security tests, unauthorized access attempts | TBD | Developers | Mitigation in progress | Roll back updates in case of security issues |

| Active Project Issues |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Issue | Impact | Priority | Assigned To | Due Date | Status H,M,L | Completed Date | Comments / Action Status |
| 6 | 3/31/2025 | Appointment Cancellation/Rescheduling Logic: Based on the current timeline, the project Manager is raising concern on the logic behind the feature mentioned above. Whether to add onto scope to incur complexity or go with a straightforward first come first serve approach. | None | 1 | Emad Abbasi | 4/6/2025 | H | 4/6/2025 | Barber possesses the ability to reschedule, but appointments will be honored via first come first serve basis. Customers will not be able to reschedule and must adhere to showing up. |

| Project Change Control |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Description | Schedule Impact | Cost Impact | Status (Proposed, Approved, Rejected) | Due Date | Comments / Action Status |
| 1 | 4/7/2025 | A change control was submitted and approved to exclude the implementation of an integrated payment system (e.g., Stripe or custom API). After discussions with the team and sponsor, the decision was made to retain the barber's current offline payment method due to privacy concerns and the application not being hosted publicly. This change ensures client operations remain uninterrupted and keeps the project within scope and timeline constraints. | None | Minimal | Proposed | 4/9/2025 | After this gets approved, the app is ready to be implemented by the barber |

| Decisions Log |  |  |  |
| --- | --- | --- | --- |
| # | Date | Description | Made By |
| 1 | 1/27 | Use a bootstrap theme for front-end implementation. | Project Team |
| 2 | 1/27 | Use AWS and MySQL for technical infrastructure | Project Team |