| Project |  |  |  |
| --- | --- | --- | --- |
| Project Name: | Barber Shop Management System | Baseline Deploy Date | March 3, 2025 |
| Executive Overview: | The Barber Shop Management System will be a web-based solution enabling Carlos Zuniga, a local barber, to manage appointments, customer information, and basic business data. The goal is to streamline daily operations, reduce scheduling conflicts, and enhance customer service. | Planned Deploy Date | April 14, 2025 |

| Key Stakeholders |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sponsor(s) | Program Manager |  |  |  |  |  |  |
|  | Jose Martinez |  |  |  |  |  |  |
| Project Team Members |  |  |  |  |  |  |  |
| Project Manager | APM | Solution Architect | Lead Developer | Product Owner | Developer | Developer |  |
| Emad Abbasi | Trinity Klein | Moshood Elias | Isaiah Morales | Anthony Perla | Jeremiah Jarina | Sarah Yao |  |

| Reporting Period: | <Week of reporting: February 17th – 22nd > |
| --- | --- |

| Project Status Overview |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Prior Period | Current Period | General Changes Since Last Reporting Period: |
| Overall |  |  | Tasks are being created, approved and assigned. Everyone has access to the Kanban board. Development on the front-end UI, and initial database schema has started. Minor issues with front-end commits on GitHub, and AWS admin login for learner lab. |

| Project Status Dashboard |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No major issues or risks identified. Critical path and cost on-schedule. |  |  |  | Issues or risks have been identified with potential impact to critical path and costs. |  | Issues or risks have been identified with clear impacts to the critical path and costs; lack of a plan that identifies critical path. |
|  |  | Prior Period |  | Current Period |  |  |  |  |  |
| Overall |  |  |  |  | The team meets twice a week to go over the project. The team meets with the program manager to discuss work items and work out any issues. |  |  |  |  |
| Schedule: |  |  |  |  | Each team member is assigned tasks. Everyone is doing their tasks on time. The project deadline is fixed. Minor issues with front-end commits on GitHub, and AWS admin login for learner lab. No impact on project deadlines. |  |  |  |  |
| Budget: |  |  |  |  | Budget is allocated well. There is no risk in the budget of the project. No added costs or monthly costs. |  |  |  |  |
| Scope: |  |  |  |  | The project charter is in progress. The development of the frontend and backend has started. ERD is on its first draft. Kanban board is updated to current tasks. |  |  |  |  |
| Resources: |  |  |  |  | Resources are allocated well. We have the time, skills, and knowledge to complete this project to deploy. There is no conflict. Everyone communicates professionally together. |  |  |  |  |

| Project (Short-term) Activities |  |  |
| --- | --- | --- |
| Key Activities Prior Period | Key Activities this Reporting Period | Planned Activities for Next Reporting Period |
| Designed team branding and established team communication channels. Secure sponsor and finalize project requirements. Set up ADO board, GitHub repository, and access management. Defined and documented the SDLC process, | Designed and deployed initial database schema. Implemented role-based access control. Start creating the login page UI and connect it to the backend authentication system. Conduct initial API testing for user authentication. | Develop appointment scheduling UI. Integrated database with appointment CRUD operations. Add customer profile management features. |

| Current Project Risk |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Category | Risks | Impact 1-5 | Likelihood 1-5 | Total Risk Score | Mitigation | Risk Trigger | Risk Trigger Date | Risk Mitigation Owner | Risk Status | Comments / Action Status |
| 1 | Resource | Limited availability of test user and dummy data | 3 | 3 | Medium | Engage early test users from various sources. | Testing phase | TBD | Project Manager | Mitigation | Use free resources and AWS Learner Labs to our advantage. |
| 2 | Technical | Unfamiliarity with scheduling algorithms | 4 | 3 | High | Research and test available libraries | Backend development phase | TBD | Developers | Mitigation | Keep it simple, but effective. |
| 3 | Technical | Potential integration challenges between backend and frontend | 4 | 3 | High | Establish clear API documentation and conduct early testing | Development phase | TBD | Developers | Monitoring | Early integration tests have been planned. |
| 4 | Schedule | Project schedule delays possible due to lack of defined timelines | 4 | 4 | High | Finalize and document project schedule | Missed internal deadlines, undefined milestones | TBD | Project Manager | Open | Adjust development phases as needed. |
| 5 | Security | Potential possibility with a data breach of client information | 3 | 5 | Medium | Implement strong authentication, and conduct security testing | Failed security tests, unauthorized access attempts | TBD | Developers | Mitigation in progress | Roll back updates in case of security issues |

| Active Project Issues |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Issue | Impact | Priority | Assigned To | Due Date | Status H, M, L | Completed Date | Comments / Action Status |
| 1 | 2/19/25 | AWS admin login issue: Members are experiencing difficulties logging into the AWS academy. | M | M | Isaiah | 2/23/2025 | M | 2/3/2025 | Solved |
| 2 | 2/19/25 | Commit Front-End Issue: Front End Developer, Jeremiah was unable to commit front-end code to GitHub | M | M | Moshood | 2/23/2025 | M | 2/24/2025 | Solved |

| Project Change Control |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Description | Schedule Impact | Cost Impact | Status (Proposed, Approved, Rejected) | Due Date | Comments / Action Status |
| N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

| Decisions Log |  |  |  |
| --- | --- | --- | --- |
| # | Date | Description | Made By |
| 1 | 1/27 | Use a bootstrap theme for front-end implementation. | Project Team |
| 2 | 1/27 | Use AWS and MySQL for technical infrastructure | Project Team |