| Project |  |  |  |
| --- | --- | --- | --- |
| Project Name: | Barber Shop Management System | Baseline Deploy Date | March 3, 2025 |
| Executive Overview: | The Barber Shop Management System will be a web-based solution enabling Carlos Zuniga, a local barber, to manage appointments, customer information, and basic business data. The goal is to streamline daily operations, reduce scheduling conflicts, and enhance customer service. | Planned Deploy Date | April 14, 2025 |

| Key Stakeholders |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sponsor(s) | Program Manager |  |  |  |  |  |  |
|  | Jose Martinez |  |  |  |  |  |  |
| Project Team Members |  |  |  |  |  |  |  |
| Project Manager | APM | Solution Architect | Lead Developer | Product Owner | Developer | Developer |  |
| Emad Abbasi | Trinity Klein | Moshood Elias | Isaiah Morales | Anthony Perla | Jeremiah Jarina | Sarah Yao |  |

| Reporting Period: | <Week of reporting: March 17th – 21st > |
| --- | --- |

| Project Status Overview |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Prior Period | Current Period | General Changes Since Last Reporting Period: |
| Overall |  |  | The login API with hashing and routing links is complete. There are potential major issues with integration to the backend database. This may have clear and major impacts to the planned deploy date. The front-end deployment is nearly complete. |

| Project Status Dashboard |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No major issues or risks identified. Critical path and cost on-schedule. |  |  |  | Issues or risks have been identified with potential impact to critical path and costs. |  | Issues or risks have been identified with clear impacts to the critical path and costs; lack of a plan that identifies critical path. |
|  |  | Prior Period |  | Current Period |  |  |  |  |  |
| Overall |  |  |  |  | The team meets twice a week to go over the project. The team meets with the program manager to go over relevant work items and tasks. Potential setbacks with application integration. |  |  |  |  |
| Schedule: |  |  |  |  | There are potential major issues with integration to the backend database. This may create clear impacts to the planned deploy date. The front-end deployment is nearly complete. |  |  |  |  |
| Budget: |  |  |  |  | Budget is allocated well. There is no risk in the budget of the project. No monthly costs, no added costs. |  |  |  |  |
| Scope: |  |  |  |  | The login API with hashing and routing links is completed. Front-end integration is delayed. Backend integration is delayed and has not yet been started. |  |  |  |  |
| Resources: |  |  |  |  | Resources are allocated well. We have the time, skills, and knowledge to complete this project to deploy. There is no conflict. Everyone communicates professionally together. |  |  |  |  |

| Project (Short-term) Activities |  |  |
| --- | --- | --- |
| Key Activities Prior Period | Key Activities this Reporting Period | Planned Activities for Next Reporting Period |
| Designed and deployed initial database schema. Implemented role-based access control. Start creating the login page UI and connect it to the backend authentication system. Conduct initial API testing for user authentication. | Develop appointment scheduling UI. Integrated database with appointment CRUD operations. Add customer profile management features. | Complete full integration of appointment scheduling UI with backend logic. Conduct internal team testing of authentication and scheduling functions. Enhance customer profile management features. Conduct mid-sprint testing and gather feedback for adjustments. |

| Current Project Risk |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Category | Risks | Impact 1-5 | Likelihood 1-5 | Total Risk Score | Mitigation | Risk Trigger | Risk Trigger Date | Risk Mitigation Owner | Risk Status | Comments / Action Status |
| 1 | Resource | Limited availability of test user and dummy data | 3 | 3 | Medium | Engage early test users from various sources. | Testing phase | TBD | Project Manager | Mitigation | Use free resources and AWS Learner Labs to our advantage. |
| 2 | Technical | Unfamiliarity with scheduling algorithms | 4 | 3 | High | Research and test available libraries | Backend development phase | TBD | Developers | Mitigation | Keep it simple, but effective. |
| 3 | Technical | Potential integration challenges between backend and frontend | 4 | 3 | High | Establish clear API documentation and conduct early testing | Development phase | TBD | Developers | Monitoring | Early integration tests have been planned. |
| 4 | Schedule | Project schedule delays possible due to lack of defined timelines | 4 | 4 | High | Finalize and document project schedule | Missed internal deadlines, undefined milestones | TBD | Project Manager | Open | Adjust development phases as needed. |
| 5 | Security | Potential possibility with a data breach of client information | 3 | 5 | Medium | Implement strong authentication, and conduct security testing | Failed security tests, unauthorized access attempts | TBD | Developers | Mitigation in progress | Roll back updates in case of security issues |

| Active Project Issues |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Issue | Impact | Priority | Assigned To | Due Date | Status H,M,L | Completed Date | Comments / Action Status |
| N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

| Project Change Control |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Description | Schedule Impact | Cost Impact | Status (Proposed, Approved, Rejected) | Due Date | Comments / Action Status |
| N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

| Decisions Log |  |  |  |
| --- | --- | --- | --- |
| # | Date | Description | Made By |
| 1 | 1/27 | Use a bootstrap theme for front-end implementation. | Project Team |
| 2 | 1/27 | Use AWS and MySQL for technical infrastructure | Project Team |