| Project |  |  |  |
| --- | --- | --- | --- |
| Project Name: | Barber Shop Management System | Baseline Deploy Date | March 3, 2025 |
| Executive Overview: | The Barber Shop Management System will be a web-based solution enabling Carlos Zuniga, a local barber, to manage appointments, customer information, and basic business data. The goal is to streamline daily operations, reduce scheduling conflicts, and enhance customer service. | Planned Deploy Date | April 14, 2025 |

| Key Stakeholders |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sponsor(s) | Program Manager |  |  |  |  |  |  |
|  | Jose Martinez |  |  |  |  |  |  |
| Project Team Members |  |  |  |  |  |  |  |
| Project Manager | APM | Solution Architect | Lead Developer | Product Owner | Developer | Developer |  |
| Emad Abbasi | Trinity Klein | Moshood Elias | Isaiah Morales | Anthony Perla | Jeremiah Jarina | Sarah Yao |  |

| Reporting Period: | <Week of reporting: March 24th – 28th > |
| --- | --- |

| Project Status Overview |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Prior Period | Current Period | General Changes Since Last Reporting Period: |
| Overall |  |  | The front-end feature of the application is largely complete. The core UI features are in place in the application. The backend integration is in progress – allowing for potential delays. |

| Project Status Dashboard |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No major issues or risks identified. Critical path and cost on-schedule. |  |  |  | Issues or risks have been identified with potential impact to critical path and costs. |  | Issues or risks have been identified with clear impacts to the critical path and costs; lack of a plan that identifies critical path. |
|  |  | Prior Period |  | Current Period |  |  |  |  |  |
| Overall |  |  |  |  | The front-end portion of the application is largely complete. The core UI features are in place. The backend integration is in progress – allowing for the potential of delays. |  |  |  |  |
| Schedule: |  |  |  |  | There are still standing potential major setbacks with the back-end integration. The project is on schedule despite this, but the deployment date is getting closer. There are also some forms that need to be made, and other remaining work. |  |  |  |  |
| Budget: |  |  |  |  | Budget is allocated well. There is no risk in the budget of the project. No monthly costs or added costs. |  |  |  |  |
| Scope: |  |  |  |  | The front-end of the application is largely complete, with core UI features like scheduling, dashboard, and navigation in place. Backend integration is in progress, with some remaining work on API connectivity and data handling. |  |  |  |  |
| Resources: |  |  |  |  | Resources are allocated well. We have the time, skills, and knowledge to complete this project to deploy. There is no conflict. Everyone communicates professionally together. |  |  |  |  |

| Project (Short-term) Activities |  |  |
| --- | --- | --- |
| Key Activities Prior Period | Key Activities this Reporting Period | Planned Activities for Next Reporting Period |
| The login API with hashing and routing links is completed. Front-end integration needs to be completed. The payment handling method needs to be set in sone. | Complete full integration of appointment scheduling UI with backend logic. Conduct internal team testing of authentication and scheduling functions. Enhance customer profile management features. Conduct mid-sprint testing and gather feedback for adjustments. | Conduct final sprint testing. Complete any final items in the backlog (integration with frontend and backend). Gather feedback for adjustments. Finalize project documentation and deliverables. Complete project presentation. Complete technical documentation. |

| Current Project Risk |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Category | Risks | Impact 1-5 | Likelihood 1-5 | Total Risk Score | Mitigation | Risk Trigger | Risk Trigger Date | Risk Mitigation Owner | Risk Status | Comments / Action Status |
| 1 | Resource | Limited availability of test user and dummy data | 3 | 3 | Medium | Engage early test users from various sources. | Testing phase | TBD | Project Manager | Mitigation | Use free resources and AWS Learner Labs to our advantage. |
| 2 | Technical | Unfamiliarity with scheduling algorithms | 4 | 3 | High | Research and test available libraries | Backend development phase | TBD | Developers | Mitigation | Keep it simple, but effective. |
| 3 | Technical | Potential integration challenges between backend and frontend | 4 | 3 | High | Establish clear API documentation and conduct early testing | Development phase | TBD | Developers | Monitoring | Early integration tests have been planned. |
| 4 | Schedule | Project schedule delays possible due to lack of defined timelines | 4 | 4 | High | Finalize and document project schedule | Missed internal deadlines, undefined milestones | TBD | Project Manager | Open | Adjust development phases as needed. |
| 5 | Security | Potential possibility with a data breach of client information | 3 | 5 | Medium | Implement strong authentication, and conduct security testing | Failed security tests, unauthorized access attempts | TBD | Developers | Mitigation in progress | Roll back updates in case of security issues |

| Active Project Issues |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Issue | Impact | Priority | Assigned To | Due Date | Status H, M,L | Completed Date | Comments / Action Status |
| N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

| Project Change Control |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # | Date | Description | Schedule Impact | Cost Impact | Status (Proposed, Approved, Rejected) | Due Date | Comments / Action Status |
| N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

| Decisions Log |  |  |  |
| --- | --- | --- | --- |
| # | Date | Description | Made By |
| 1 | 1/27 | Use a bootstrap theme for front-end implementation. | Project Team |
| 2 | 1/27 | Use AWS and MySQL for technical infrastructure | Project Team |