## RACI Matrix
Usage and Management - RACI Matrix ITSM Operations / ITSM Managed Services
R = Responsible | The person that is responsible for producing the deliverable. There can only be 1 person/level that is responsible.
A = Accountable | The person that is accountable for the deliverable, ensures the work is completed. There can only be 1 person/level that is accountable.
C = Consulted / Contributes | The person or persons that must be consulted before a decision or action can be made.
I = Informed | The person or persons must be informed of any decision or action that has been made.
| ITSM Remedy Application Support |  |  |  |  | ITSM Operations |  | <Innov8 / Team 3>
| Lead Developer | Architect | Developer #1 | Developer #2 | PM | APM | Product Owner
1. Decide team cadence (Project Management) |  |  |  |  | A/R | C | C
1a. Research Agile team cadence best practices |  |  |  |  | R | C
1b. Schedule and confirm meeting times |  |  |  |  | A/R | C | I
1c. Document team cadence |  |  |  |  | R | A | I
2. Design team branding (Project Management) |  |  |  |  | A | R | C
2a. Brainstorm team name, colors, branding | C | C | C | C | A | R | C
2b. Create logo and branding assets |  |  | R |  | A | C | C
2c. Finalize and approve branding |  |  |  |  | C | R | A
3. Decide PM methodology (Project Management) |  |  |  |  | A/R | C | C
3a. Research Agile methodologies |  |  |  |  | R | C
3b. Discuss and decide methodology | C | C | C | C | A/R | C | C
3c. Document selected methodology |  |  |  |  | R | A | I
4. Get a sponsor strategy (Project Management) |  |  |  |  | A | R | C
4a. Research outreach methods |  |  |  |  | C | R | C
4b. Draft sponsor outreach message |  |  |  |  | C | R | A
4c. Assign team member for communication |  |  |  |  | A | R | C
5. Set up technical infrastructure (Development) | C | A/R | C | C | I | I | I
5a. Configure Azure DevOps board | C | A | R | C | C | I | I
5b. Set up communication channels | C | A | R | C | C | I | I
5c. Ensure member access | C | A/R | I | I | C | I | I
6. Get a GitHub repository setup (Development) | C | A/R | C | C | I | I | I
6a. Create GitHub repository | C | A/R | I | I | I | I | I
6b. Set up branching strategy | A | R | C | C | I | I | I
6c. Invite team members and test access | C | A/R | I | I | I | I | I
7. Document SDLC process (Development) | C | A | C | C | R | C | C
7a. Draft SDLC document | C | A | C | C | R | C | C
7b. Research and define SDLC approach | C | A | C | C | R | C | C
7c. Finalize and store document | C | A | I | I | R | C | C
8. Implement User Authentication (Development) | A | C | R | C | I | I | I
8a. Convert password to hash | A | C | R |  | I | I | I
8b. Implement token-based authentication | A | C | R | C | I | I | I
8c. Implement role-based authentication | A | C | R | C | I | I | I
9. Implement Role-Based Access Control (Development) | A | C | C | R | I | I | C
9a. Admin role implementation | A | C | C | R | I | I | C
9b. Customer role implementation | A | C | C | R | I | I | C
9c. Barber role implementation | A | C | C | R | I | I | C
10. Set Up Database Schema (Development) | C | A/R | C | C | I | I | C
10a. Design ERD for database | C | A/R | C | C | I | I | C
10b. Define and create tables | C | A | C | C | I | I | I
10c. Implement relationships | C | A | R | C | I | I | I
11. Create Appointment Scheduling UI (Development) | A | C | C | R | I | I | C
11a. Develop front-end form | A | C | C | R | I | I | C
11b. Implement responsive UI | A | C | C | R | I | I | C
11c. Integrate UI with backend API | A | C | C | R | I | I | C
12. Develop Appointment CRUD Operations (Development) | A | C | R | C | I | I | C
12a. Create backend API | A | C | R | C | I | I | C
12b. Implement appointment validation | A | C | R | C | I | I | C
12c. Connect database with front-end UI | A | C | R | C | I | I | C
12d. Test CRUD operations | A | C | R | R | I | I | C
13. Customer Profile Management (Development) | A | C | C | R | I | I | C
13a. Develop UI for customer information | A | C | C | R | I | I | C
13b. Implement backend logic | A | C | R | C | I | I | C
13c. Secure customer information | A | C | R | C | I | I | C
13d. Create customer history tracking | A | C | R | C | I | I | C
14. Appointment Notifications (Development) | A | C | R | C | I | I | C
14a. Implement email notification system | A | C | R | C | I | I | C
15. Reporting Dashboard | A | C | R | C | I | I | C
15a. Design and implement UI | A | C | C | R | I | I | C
15b. Add filters for customized reporting | A | C | R | C | I | I | C
16. Conduct User Acceptance Testing (Project Management) | C | C | C | C | A | R | C
16a. Define test scenarios | C | C | C | C | A | R | C
16b. Perform UAT with stakeholders | C | C | C | C | A | R | C
16c. Collect feedback and document issues | C | C | C | C | A | R | C
16d. Resolve UAT-reported issues | A | C | R | R | C | C | I
17. Finalize Documentation & Presentation (Project Management) | C | C | C | C | A | R | C
17a. Complete technical documentation | A | C | R | R | C | C | I
17b. Prepare user guide | C | C | R | R | A | C | C
17c. Create final capstone presentation | C | C | C | C | A | R | C
17d. Conduct final team review | C | C | C | C | A | R | C
Role/Team
Activity/Deliverable

## Definitions
R = Responsible | The person that is responsible for producing the deliverable. There can only be 1 person/level that is responsible.
A = Accountable | The person that is accountable for the deliverable, ensures the work is completed. There can only be 1 person/level that is accountable.
C = Consulted / Contributes | The person or persons that must be consulted before a decision or action can be made.
I = Informed | The person or persons must be informed of any decision or action that has been made.