## Risks
Risk Management Matrix (Risk Register)
Project |  |  | Barbershop Management System | [5 empty] | Project # | 1001
Project manager |  |  | Emad Muhammad Abbasi | [5 empty] | Sponsor | Carlos Zuniga
Project artifacts | [8 empty] | Updated | 2025-02-21
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | Team is unfamiliarity with scheduling algorithms may cause development delays. | 3 | 4 | 3 | 72 | Technical | Slow development progress, repeated errors in scheduling logic | Research existing libraries, consult experts, conduct prototype testing | Adjust project timeline to allow for testing | Dev Team | Monitoring | 2025-02-21 | 2025-04-12
2 | There is a limited availability of test users from barber shop clientele | 3 | 3 | 4 | 72 | Resource | No feedback from users, testing phase delayed | Engage early testers, offer incentives | Use simulated test data if needed | Project Manager | Mitigation in progress | 2025-02-21 | 2025-04-12
3 | There is potential integration challenges between backend and frontend | 3 | 4 | 3 | 72 | Technical | API failures, front-end errors during integration | Establish clear API documentation, conduct early integration testing | Assign a dedicated developer for API troubleshooting | Lead Developer | Monitoring | 2025-02-21 | 2025-04-12
4 | There may be project schedule delays due to lack of defined timelines | 4 | 4 | 2 | 64 | Schedule | Missed internal deadlines, undefined milestones | Finalize and document project schedule | Adjust development phases if necessary | Project Manager | Open | 2025-02-21 | 2025-04-12
5 | There may be user authentication vulnerabilities could lead to data breaches | 3 | 5 | 3 | 90 | Security | Failed security tests, unauthorized access attempts | Implement strong authentication (JWT, 2FA), conduct security testing | Roll back updates in case of security issues | Dev Team | Mitigation in progress | 2025-02-21 | 2025-04-12
Note on C6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on L6: Options are: Open Closed