## Risk Assessment
Project Risk Log
# | Category | Risks | Impact 1-5 (ignoring controls) | Likelihood 1-5 (ignoring controls) | Total Risk Score Low = 1-7 Med = 8-15 High = 16-25 | Mitigation | Risk Trigger | Risk Trigger Date | Risk Mitigation Owner | Risk Status | Comments / Action Status
1 | Technical | Team is unfamiliarity with scheduling algorithms may cause development delays. | 4 | 3 | Medium | Adjust project timeline to allow for testing | Slow development progress, repeated errors in scheduling logic | 2025-02-15 | Dev Team | Monitoring | Research existing libraries, consult experts, conduct prototype testing
2 | Resource | There is a limited availability of test users from barber shop clientele | 3 | 3 | Low | Use simulated test data if needed | No feedback from users, testing phase delayed | 2025-03-10 | Project Manager | Mitigation in progress | Engage early testers, offer incentives
3 | Technical | There is potential integration challenges between backend and frontend | 4 | 3 | Medium | Assign a dedicated developer for API troubleshooting | API failures, front-end errors during integration | 2025-03-01 | Lead Developer | Monitoring | Establish clear API documentation, conduct early integration testing
4 | Requirements / Scope | There may be project schedule delays due to lack of defined timelines | 4 | 4 | High | Adjust development phases if necessary | Missed internal deadlines, undefined milestones | 2025-02-01 | Project Manager | Open | Finalize and document project schedule
5 | Info Security | There may be user authentication vulnerabilities could lead to data breaches | 5 | 3 | Medium | Roll back updates in case of security issues | Failed security tests, unauthorized access attempts | 2025-04-05 | Dev Team | Mitigation in progress | Implement strong authentication (JWT, 2FA), conduct security testing
Note on B2: Step 1: Select appropriate Risk Category from dropdown. If you would like to see additional values, please contact the PMO.
Note on C2: Step 2: Describe the Program / Project Risk. They can be existing or an anticipated event occurring at a later time.
Note on D2: Step 3: Enter the Impact level of the risk. Score should ignore any mitigation plans. See Probably Scale for guidelines.
Note on E2: Step 4: Enter the Likelihood level of the risk. This is the probability of the specific risk becoming realized with existing mitigation plans.
Note on F2: Step 5: All High and Med risks must identify mitigation steps to address the risk. Low risks should also be discussed.
Note on G2: Step 6: Describe if any existing controls exists to mitigate the risk. These can be process, procedures, implemented plans that address the risk. If there are none, then describe mitigation actions to address the risks.
Note on H2: Step 7: Describe the trigger that will prompt the execution of the mitigation steps.
Note on I2: Step 8: Identify the estimated risk trigger date. This could be a range.
Note on J2: Step 9: Identify the risk owner responsible for monitoring and addressing the risk.
Note on K2: Step 10: Identify whether the risk is Averted/Closed = Risk not realized Resolved = Risk addressed through mitigation actions. Monitoring = Risk being monitored, no action applied yet. Mitigation in Progress = Being addressed through mitigation actions Issue = Risk realized and turned into issue.
Note on L2: Step 11: Provide details on the status of the risk, mitigation actions and resolution.

## Risk Categories (hidden)
Risk Categories (***Step 1***)
Business Process
Communication
Data Quality
Finance
Hardware
Implementation
Info Security
Integration
Network
Procurement
Project Management
Regulatory / Legal
Requirements / Scope
Resource
Software
System Performance
Technical
Testing
Vendor

## Risk Scale
Impact - Scale (***Step 3***)
Impact Criteria | 1 | 2 | 3 | 4 | 5
Excessive Costs, Loss of Revenue, or Erroneous Financial Stmts | <=$50K | > $50K and <= $100K | > $100k and <= $150K | > $200k and <= $250K | >=$250
Legal or Regulatory Compliance | In compliance | N/A | N/A | N/A | Not in Compliance
Erroneous Management Information | Information does not impact decision-making |  | Information is helpful, not critical for decision-making |  | Information is critical for decision-making
Project / Program Success | Critical Success Criteria isn't affected |  | Critical Success Criteria is affected; not a Showstopper |  | Critical Success Criteria is not met; SHOWSTOPPER
Project / Program Interruption or Schedule Impacted | Low Severity (for project, 1-2 milestones affected, minor schedule impact) (for program, only affects one project) | Low-Med Severity (for project, schedule impact <5%) | Medium Severity (for project, schedule impact of 5-10%) (for program, affects more than one project) | Med-High Severity (for project, schedule impact 10%-15%) | Program Stop or pushout (for project, schedule impact > 15%)
Biz Interruption | Low Severity (Manual process could recover) |  | Medium Severity (Combination of manual process and work arounds) |  | High Severity or Business Stop
Likelihood - Scale (***Step 4***)
Likelihood Criteria | 1 | 2 | 3 | 4 | 5
Probability | 1% - 20% | 20% - 40% | 40% - 60% | 80% - 80% | 80% - 100%
Descriptive | Remote (no issues today) | Probable | High Probability (process is manual; human intervention) | High Certainty | Certain (known issues today; tool or process is new; no expertise)

## Common Risks - Guide
Common Risks (Not an exhaustive list)
Risk Category | Common Risks | Common Controls / Mitigation
Business Process | Key control processes are not clearly defined, documented or communicated, therefore not sustainable
Business Process | SLA's are not formally established and agreed-upon for critical processes with customers (internal or external) and or suppliers.
Business Process | Formal change control is not applied to key business processes or interdependent operations.
Communication | Key decisions around deliverables are not communicated up/down with project team. | Review of Communication plan with project team during planning phase.
Communication | Senior leadership is not aware of milestone progress or issues/risks.
Communication | Key stakeholders are not informed of key product scope changes or schedule updates.
Data Quality | Critical pieces of data are changed in key database tables. | Audit log retained of all changes and who made them. History of data retained.
Data Quality | Target data extract does not match source data. | Automatic reconciliation
Data Quality | Current SOR (System of Record) inaccurate. Key business functions that rely on this data cannot function at acceptable levels of accuracy. | Validate data quality / Process embeds controls to validate data
Data Quality | Overall data quality in suspect / inaccurate
Hardware | Availability of sufficient hardware for data storage.
Hardware | Addition and build of new boxes do not meet targeted milestone delivery dates.
Implementation | Business groups will not be able to support the implementation due to lack of resources, training, other priorities, or volume of other changes.
Implementation | Training material is ineffective, does not address local customs or languages, is not available online, or is not ready prior to implementation.
Implementation | Product support training, support or resources are not at the level necessary to support the implementation.
Info Security | Personally Identifiable Information (PII) is handled / stored within your group's systems, processes, or third party vendors and compliance with Security policies are not proactively monitored or validated.
Info Security | Hardware / software not to IS&T standard. Likely problems with passing the InfoSec Scan.
Integration | Dependencies on other projects and or deficient change control could impact integration efforts.
Integration | Level of complexity for the integration effort is not fully identified, planned or anticipated.
Network | Performance across network does not meet specified expectations | Network team engaged to identify alternatives
Network | New networking or telephony technology will be implemented resulting in potential integration issues.
Network | Data and Service Resiliency does not meet specified success criteria
Performance | Performance issues cause key batch cycles to miss their window on semi-routine basis.
Performance | System performance is impacted due to volume growth, server capacity, network / communications issues, or application / database design.
Performance | Solution performance does not meet specified success criteria
Procurement | Supplier selection unauthorized
Procurement | Supplier decisions are not based on lowest total cost/best value
Procurement | Goods / services provided by suppliers do not meet spec/customer requirements or IS&T standards
Project management | Insufficient resources assigned to support the product development. Deployment schedule slips. | Coordination meetings / Common release schedule
Project management | Lack of key SME / technical resources to construct the right solution for the business | Requested support from internal resources.
Project management | Significant risks around the new process are not identified or addressed
Project management | A small change had significant impact to key buiness processes. This change is not recognized as significant. | Detailed design reviews with business stakeholders who understand the details.
Project management | Performance to key project deliverables not adequately tracked – problem area not identified – program deployment delayed. | Regular reviews of Project Plans with development team
Project management | Project tracking not at the right level of detail – impossible to determine whether performance is truly effective in meeting needs | Utilize work breakdown structure to determine appropriate level of detail required for project tracking.
Project management | Key stakeholders/review bodies do not have visibility or awareness of project timeline and deliverables
Project management | Milestone/deliverables not visible/available for support groups not directly tied to the project.
Project management | Project/Program decision makers missing key stakeholder
Project management | Individuals gathering requirements lack business knowledge or experience – key functionality is missed in their search.
Requirements/Scope | Requirements and project scope continue to change and formal change control is not followed. | Establish change review board and utilize version control.
Project management | Key stakeholder group is missed. Therefore, key issues are never flagged.
Project management | Inadequate resources assigned to your program, preventing a comprehensive testing. Major issues missed.
Project management | Design/Development problems delay preceeding activities resulting in loss of committed resource
Project management | Real world data for testing of business scenarios is not available or cannot be completely simulated in the test environment.
Project management | Product Deliverable does not meet customer requirements | Product Rqmt signoff
Project management | Communications with key stakeholders and or review bodies is difficult and approval or feedback is lacking.
Regulatory / Legal | Inappropriate or destructive data/systems changes can be made in production environments without the ability to trace changes to a specific user via inappropriate access to batch programs.
Software | Uncertainties about the software leads to production/configuration delays
Software | Uncertainties about the software leads to last minute major design changes as software limitations are finally understood
Technical | Straddle of new/existing applications creates a great deal of work for the existing business unit – workload beyond their capability to complete in the straddle period
Testing | User testing environment are not adequately set up for application testing.
Testing | Business use cases do not test key scenarios leading to data/application issues after production release.
Testing | Lack of business resources to participate in User Acceptance Testing leading to No Go for release.