## Cover
Requirements Traceability Matrix
Program | Innov8
Project | Barbershop Management System
Revision History
Date | Revision # | Author | Description of Change
| 0.01 | Trinity Klein | Initial draft

## Funtional Reqs
ID | Requirement Title/Name | Requirement Description | Category/Type | Status | Priority (H/M/L) | Source
1 | Appointment Management | System must be able to allow barber (user) to book reschedule or cancel appointments. It must display the available time slots based on the barber's schedules. | Operational | Complete | H | Frontend Developer
2 | Service Management | System must be able to define and update services. | Operational | Complete | H | Development Team
3 | Availability Management | System must be able to allow the barber to set their working hours, and breaks. It must prevent double-booking. | Operational | Complete | H | Development Team
4 | Payment Integration | System must be able to allow customers to pay via Squarespace and Zelle. | Operational | Out-of-Scope | M | Development Team
5 | Customer Management | System must be able to store customer information and booking history. | Archive | Complete | H | Development Team
6 | Barber Dashboard | System must allow the barber to view and manage appointments. It must be able to track work schedules. | Operational | Complete | H | Frontend Developer
7 | Usability | System must be able have a user-friendly interface for customer and barbers. | Design | Complete | M | Frontend Developer
8 | Data Backups | System must have regular data backups to prevent data loss in case of a failure. | Security | Complete | M | Backend Developer
9 | Performance | System must be able to handle multipe users on the system simultaneoously without slowing down. | Performance | Complete | L | Systems Architect
10 | Barber Management | System must allow user to see, create, delete, and update barbers. | Operational | Complete | H | Backend Developer
11 | Exportable Reports | System must allow user to export history of appointments. | Operational | Complete | M | Frontend Developer
12 | Dashboard | System must allow user to view statuses, recent appointments, and data from home screen of system portal. | Operational | Complete | M | Backend Developer
13 | User Login | System must allow user to access portal through use of username and password. | Security | Complete | H | Backend Developer, Frontend Developer
14 | Admin Portal | System must have an accessable dashboard for managing all system features. (Ex.Adding apponitments, deleting services, etc. | Operational | Complete | H | Frontend Developer
15 | Users Management | System must allow user to see, create, delete, and update users. | Operational | Complete | M | Backend Developer
16 | Customer Scheduling | System must allow customers to book an appointment based on time and availability. | Operational | Complete | H | Backend Developer, Frontend Developer
17 | Portal Search Functionality | System must allow users to search through appointment history, services, customers, barbers, and users by parameters. | Operational | Complete | M | Frontend Developer

## Non-Functional Reqs
ID | Category | Type | Requirement Name | Requirement Description | Status | Priority (H/M/L) | Soruce
1.0 Look and Feel
1.01 | Look and Feel | Performance | Fast Load Time | Each page should load within 3 seconds under standard network conditions to improve user experience and reduce bounce rates | Complete | M | Backend Developer
1.02 | Look and Feel | Interactivity | Smooth Page Transitions | page transitions (navigating between pages) should be smooth with no noticeable lag or tearing. | Complete | M | Front-end Developer
1.03 | Look and Feel | Responsiveness | Mobile Friendly Design | The webpage must adjust to different screen sizes (phone and tablets) without losing functionality or visual. | Complete | M | Front-end Developer
1.04 | Look and Feel | Aesthetic | Color Scheme | The color scheme should follow the brand guidelines, with high contrast for readability and accessibility | Complete | M | Front-end Developer
1.05 | Look and Feel | Consistency | Consistent Layout | The layout and visual elements (ex: buttons and icons) should remain consistent throughout all pages to create a professional design | Complete | M | Sponsor
1.06 | Look and Feel | Aesthetic | Dark Mode Option | The dashboard should have a dark mode setting | Complete | M | Front-end Developer
2.0 Usability and Human Factors
2.01 | Usability and Human Factors | Convenience | Easy Navigation | Navigation should be have clear menus and categories allowing users to find information with no more than 3 clicks. | Complete | M | Frond-end Developer
2.02 | Usability and Human Factors | Accessibility | Screen Reader Compatibility | The website should be fully compatible with screen readers, including proper use of alt tags for images and descriptive for all interactive elements. | Complete | H | Development Team
2.03 | Usability and Human Factors | Correctness/Accuracy | Data Accuracy | All data displayed on the webiste (ex. Book Appointments) must be accurate and updated regularly to avoid errors | Complete | H | Backend Developer
2.04 | Usability and Human Factors | Documentation: suitability and sufficiency of explanatory descriptive information. | Clear Instructions | The website should provide tips explaining users on how to navigate, book an appointment, or any interactive features in the website | Complete | M | Development Team
2.05 | Usability and Human Factors | Operability: can be operated in a reliably efficient manner | Reliable Functionality | All buttons and buttons must function as intended without any errors and any potential issues should be resolved within 24 hours of discovery | Complete | H | Development Team
2.06 | Usability and Human Factors | Efficiency | Quick Booking Process | Users should be able to book an appointment in no more than 10 steps | Complete | M | Development Team
3.0 Maintainability and Support
3.01 | Maintainability and Support | Bug Tracking | Issues Reporting System | Customers should be able to report bugs regarding the website through a dedicated form | Complete | M | Development Team
3.02 | Maintainability and Support | Version Control | Git Hub Repository | The code should be managed using Git for tracking changes and rollbacks | Complete | H | Development Team
3.04 | Maintainability and Support | Monitoring | Error Logging | The system should log errors and provide notifications for failed proces. | Complete | H | Development Team
3.05 | Maintainability and Support | Backup | Automated Backups | Database and assets should be backed up daily | Complete | H | Development Team
4.0 Operational
4.01 | Operational | Reliability | Available 24/7 | The website should maintain 96.999% | Complete | L | Development Team
4.02 | Operational | Security | Auto-Logoff | Barbers should be logged out after 30 minutes inactivity | Complete | L | Development Team
4.03 | Operational | Compliance | User Data Privacy | Customesr/Barbers data (especially passwords) should be encrypted and stored securely | Complete | H | Backend Development
4.04 | Operational | Maintenance | Downtime Notification | Users should be notified about scheduled maintenance | Complete | L | Development Team
5.0 Performance
5.01 | Performance | Server Response | API Response Time | All API Requests should return not more than 10 seconds under normal load conditions | Complete | L | Backend Development
5.02 | Performance | Capacity | Concurrent User | The application should support up to 400 concurrent users without performance issue | Complete | L | Development Team
5.03 | Performance | Database | Querying Speed | All database queries should be optimized to execute in under 500 ms | Complete | L | Backend Development
6.0 Network Services
6.01 | Security | Website Protection | HTTPS Encryption | Both Dashboard and Webpage must use HTTPS | Complete | H | Development Team
7.0 Security
7.01 | Security | Authorization | Role-based Access Control | Barbers must have a restrcited access to Customer data and admin functions based on user roles (admin & barber roles) | Complete | H | Development Team
7.02 | Security | Password Protection | Password Encryption | All password must be using hasing algorithms such as SHA-256 or bcrypt) | Complete | H | Development Team
8.0 Regulatory/Legal
8.01 | Regulatory/Legal | Terms & Condition | User Agreement | Users must accept the website's Terms and Conditions before booking appointments or making payments | Complete | M | Development Team
9.0 Safety
9.01 | Safety | Physical Safety | No Harm or Injury | The website and dashboard shoud not cause physical harm such as seizure inducing flashing elements. | Complete | M | Frontend Development
10.0 Reporting/Archive
10.01 | Archieve | User History | Appointments & Transaction History | The dashboard should have a record of past appointments and transaction function | Complete | H | Development Team
10.02 | Reproting | Dashboard Metrics | Analytics & Insight | The dashboard must provide reports on appointments and customer trends | Complete | L | Frontend Development
There is no one single correct way to document non-functional requirements. The way you choose should support your objectives of making sure that all requirements are designed into the solution and whatever way achieves this best is the correct way. Please add or remove relevant items as needed, but do not duplicate process, data or functional requirements here.