## WBS
Work Breakdown Structure
Project |  | Barber Shop Management System |  |  |  | Project # | 1001
Project Manager |  | Emab Abbasi |  |  |  | Sponsor | Carlos Zuniga
Project Artifacts | [5 empty] | Updated | 2025-04-13
ID | Task | Dependencies | Status | Effort Hours | Cost | Start Date | Planned Completion | Estimate to Completion | Actual Completion | Resource
1 | Decide team cadence |  | Completed | 5 | 0 | 2025-02-03 | 2025-02-05 | 0 | 2025-02-05 | Emad Abbasi
2 | Design Team Branding |  | Completed | 6 | 0 | 2025-02-03 | 2025-02-06 | 0 | 2024-02-06 | Jermiah Jarina
3 | Decide PM methodolgy |  | Completed | 4 | 0 | 2025-02-03 | 2025-02-04 | 0 | 2025-02-04 | Emad Abbasi
4 | Get a sponsor strategy |  | Completed | 6 | 0 | 2025-02-03 | 2025-02-07 | 0 | 2025-02-07 | Anthony Perla
5 | Set up technical infrastructure |  | Completed | 8 | 0 | 2025-02-03 | 2025-02-08 | 0 | 2025-02-08 | Emad Abbasi
6 | Get a Github repository setup |  | Completed | 4 | 0 | 2025-02-03 | 2025-02-05 | 0 | 2025-02-05 | Moshood Elias
7 | Document SDLC process |  | Completed | 5 | 0 | 2025-02-03 | 2025-02-09 | 0 | 2025-02-09 | Trinity Klein
8 | Implement User Authentication |  | Completed | 10 | 0 | 2025-02-17 | 2025-03-02 | 10 | 2025-03-02 | Sarah Yao
9 | Implement Role-Based Access Control | 8 | Completed | 12 | 0 | 2025-02-17 | 2025-03-02 | 12 | 2025-03-02 | Moshood Elias
10 | Set up Database Schema | 8 | Completed | 15 | 0 | 2025-02-17 | 2025-03-02 | 15 | 2025-03-02 | Moshood Elias
11 | Create Appointment Scheduling UI | 10 | Completed | 12 | 0 | 2025-03-03 | 2025-03-16 | 12 | 2025-03-16 | Jermiah Jarina
12 | Development Appointment CRUD operations | 10 | Completed | 14 | 0 | 2025-03-03 | 2025-03-16 | 14 | 2026-03-16 | Isaiah Morales
13 | Customer Profile Management | 10 | Completed | 10 | 0 | 2025-03-17 | 2025-03-30 | 10 | 2025-03-30 | Sarah Yao
14 | Appointment Notifications | 11 | Completed | 8 | 0 | 2025-03-31 | 2025-04-13 | 8 | 2025-04-13 | Moshood Elias
15 | Reporting Dashboard | 11 | Completed | 12 | 0 | 2025-03-31 | 2025-04-13 | 12 | 2025-04-13 | Jermiah Jarina
16 | Conduct User Acceptance Testing (UAT) | 12 | Completed | 10 | 0 | 2025-04-14 | 2025-04-27 | 10 | 2025-04-27 | Anthony Perla
17 | Finalize Documentation and Presentation | 16 | Completed | 8 | 0 | 2025-04-14 | 2025-04-28 | 8 | 2025-04-28 | Emad Abbasi and Trinity Klein
Note on D6: Options are: Open Closed